## Slide 1
ENGINEERING
COMPASS 2026
Member Chat, as a product
Chat Broker
@stellarus/member-chat SDK
Pluggable AI agents
Benefits service

## Slide 2
Current solution – no Stellarus product
TODAY · SHIPS 7/1
Non-Stellarus chat – Employees only
BSC + Genesys + Sierra using the Stellarus Benefits Service
BSC / Genesys
→
Sierra.ai
→
Hard coded rules
TARGET PRODUCT
Stellarus Chat Platform
Broker, SDK owned by Stellarus — customers integrate however they like.
01
Any channel calls one Chat Broker API
02
Broker enriches with benefits data
03
Routes to the right AI agent by product
04
Tracks conversations & escalations
RISK · Missing specialty LoB in Benefits service, plan is to release with Sierra fetching plan data from Benefits service directly.
Effort in progress to get this data added.
This connection will go away again when the platform is ready for 9/1 release.
05
Benefits service source of truth for all plans

## Slide 3
Stellarus Platform - road to 9/1 and beyond
API – Broker service
Multi agent and customers integration, telemetry, insights
Data services and Atlas IQ integration
AI Agents and data science collaboration
7/1
9/1
Beyond
9/1
Beyond
Beyond
9/1
9/1
Benefits service - All lines of business
Member service, eligibility, claims history..
Sierra.ai
Member agent
CSR agent
Beyond
UI
Demos
White labelled UI SDK

## Slide 4
Stellarus Platform – BSC Member chat with Sierra scope
Components | Status | Target deploy | Owner | Blocked by | Release
Benefits service – development work and functionality | 100% | Prod | Apps |  | 7/1
Benefits service – specialty LoB Effort to identify and structure data in progress | 10% In progress | 7/1 | Apps |  | 7/1
Genesys escalation with Sierra/BSC UI | Unknown / In progress |  | PTP |  | 7/1
API – Broker All chat connection manager, logs, storage | 75% - dev | Start July, continuous | Apps |  | 9/1
SDK - API v1 – Development, documentation, distribution | Planning | 7/15 | Apps | API | 9/1
SDK - API v2 – Genesys Escalation Understand routing rules, and Genesys API part of the scope | Not started | 8/1 | Apps | SDK V1 | 9/1
Embed Stellarus SDK in BSC work to start BSC/Non-commercial to use SDK in their UI | Not started | 8/1, start work? | Syng? | SDK | 9/1
Stellarus UI Not part of deliverables, but used for testing and demos | 70% in progress | Continuous | Apps |  | N/A

## Slide 5
Stellarus Platform – BSC Member chat – SOW / MSA Timeline
Components | Amount ($) | First Issue Date | Status | Second issue Date | Status | Third Issues Date | Suggested Action
PTP – BSC SOW 59 – Employee Benefits Integration | $90,720 | May 14th | Detail to justify the expense missing in SOW | May 26th | Further cost breakdown requested | Jun 8th | To reduce cost, remove Voice components
PTP – BSC SOW 58 – Employee Benefits voice | $52,920 | May 14th | Detail to justify the expense missing in SOW | May 26th | Further cost breakdown requested | Jun 8th | Stop effort and hold SOW
PTP – BSC SOW 57 – Employee Benefits chat | $249,480 | May 14th | Detail to justify the expense missing in SOW | May 26th | Further cost breakdown requested | Jun 8th | To reduce cost, remove Voice components
MSA in place between Stellarus and PTP |  | N/A | MSA Not signed. BAA language updated but not signed |  |  |  | 
Bridge in place to authorize work to commence, before SOW signed | N/A | N/A | No Bridge in place |  |  |  | 
Work began on work covered under the PTP SOW(s) |  | Mid April (est) | Authorization not granted to start |  |  |  | 

## Slide 6
BLOCKERS TO RESOLVE
Open risks and questions
DATA
Specialty LoB is missing from Benefits service and Sierra
Where does the data come from, and in what format? Engineering parses and adds it to the database.
Apps + Data
GENESYS
Escalation routing isn't yet understood by Stellarus
How do routing rules work, and what does the Genesys API/SDK expose? We need to surface escalation as a tracked SDK action.
Apps + PTP?
SCOPE
Is the 7/1 Sierra integration throwaway? Not entirely, it will be re-purposed
Sierra has logic and guard rails built in, these learnings will be re-used in the Stellarus AI agents
Product
UX
How does escalation feel for the member?
Start simple with an always-available button; research whether escalation should become part of the conversation.
UX + Apps

## Slide 7
Timeline for member chat release
Jul 1
Non-Stellarus Live
Sierra member chat for BSC
Benefits service – all LoB
Aug 1
Stellarus Platform | Beta
SDK with escalation
BSC integration start
Aug 15
Platform | Release candidate
Continuous testing and adjustments
Sep 1
Release
NEXT STEPS | PARALLEL WORK WITH APPS AND DATA SCIENCE TEAM
UI SDK
CSR Agent
Member Agent
Voice
July 15
Stellarus Platform | Alpha
Demo UI
SDK API