## RACI
| Benefit Quoting MVP1 Critical Activity | Core Team |  |  |  |  | Additional Build Team |  |  | Leadership Team |  |  | Additional SMEs |  |  |  | Core Team | [7 empty] | Regulatory Team |  |  |  | Leadership Team
|  | BSC Customer Experience Ops | BSC IA & AI Team | BSC Nexus Product Team | Stellarus Product | Stellarus Adv Analytics | Stellarus EA | Stellarus Nexus Team | Stellarus D&A Team | Transformation LT | Customer Care LT | Product/AI Leadership | Product Strategy | BSC Pharmacy | BSC CE QA Team | Stellarus Pharmacy | Accenture | Customer Care Management | Transformation | Stellarus AIA | Nexus Product Team | Enterprise Architect | CE and Digital Transformation | CE QA & Audit | IFP | Appeals & Grievances | Legal | Legal | Transformation LT | Customer Care LT | GenAI Leadership
|  | Greg Heather/Kerry | Deb Dab Krista Derdowski | Amy Botill Aly Guitierrez | Gabby Mirsaidi Jason Jackson Mike Beck | Mike Becker Andrew Hudson Bharath Tami Blake | Tony Begum | Robert Hassanali Kiran Kumar Jason Norsworthy Kiran Vengala | Rahul Sakpal Prasad Chaki | Bryce/Jaime | Nate/Vivian | Greg Ryslik Jayesh Patel | Kit Hansen | Chrissy Nordby | Qais Yonisi Melissa Carroll Phillip House | Dang Tran | Alicia C Raina Cheng Manthan D Kamlesh Gupta | Heather White Becca Littman | Deborah Dab Sankari Kannan | Gabrielle Mirsaidi Julie Hughes Mike Beck | Robert Hassanali Kiran Kumar Jason Norsworthy Kiran Vengala | Tony Begum | Kristina Guzikova | Qais Yonisi Melissa Carroll Phillip House | Patrice Bergman Marty Katreeb Lehi Black | Jennifer Gannon Natali Jiminez - Ascencio | Ellie Lew (Law) David Keystone (Privacy) | Amanda Knudsen( Litigation) Andrew DeClerq & Carla Small (CCA regulations) | Nate Oubre Bryce Williams | Vivian Phillips Husband Marc Harris | Gabrielle Mirsaidi Mike Becker
Discovery | Scope Approval | [8 empty] | A | I | R |  |  |  |  | R | I | R | I |  | C |  |  | R |  | R | R | A | I | R
Admin | MVP1 weekly report out and sync calls | [8 empty] | I | I | I |  |  |  |  | R | C | A | I |  | I | [6 empty] | I | I | I
Admin | BSC Leadership Report Out | [8 empty] | I | I | I | [6 empty] | A/R | A/R | [8 empty] | I | I | I
Admin | Kick-off | [17 empty] | A/R
Design | Requirements Gathering- data model and UI framework | [10 empty] | A |  |  |  |  | A/R | R | R | A | R | A | R/C | C | [6 empty] | A
Build | Data Procurement | [10 empty] | C |  |  |  |  | R | R | I | C | A | I | [8 empty] | C
Admin | Scrums, Sprint Planning and Daily Stand-up | bar: A/R to A/R A
Design | Technical Design/Solution Discussions including UI/UX design if needed for formulary | bar: A/R to A/R A
Design | Technical Design Documentation | [10 empty] | A |  |  |  |  | R | I | I | A | R | A | [8 empty] | A
Build | Access Provisioning to the Dev environment | [10 empty] | A/R |  |  |  |  | A/R | I | I | A/R | A/R | I | [8 empty] | A/R
Build | Model Build | [10 empty] | A/R |  |  |  |  | A/R | C | C | C | C | A/R | [8 empty] | A/R
N/A - done | Nexus Integration | [10 empty] | A/R |  |  |  |  | A/R | C | C | C | A/R | A/R | [8 empty] | A/R
N/A - done | Chat-like UI Build and Nexus Integration | [10 empty] | A/R |  |  |  |  | A/R | C | C | C | A/R | A/R | [8 empty] | A/R
Build? | Model Eval & Human Validation Testing | [10 empty] | A |  |  |  |  | C | A/R | A/R | C | C | A |  | R | [6 empty] | A
Build | Optimization and Retesting | [10 empty] | A |  |  |  |  | R | A/R | A/R | A | C | A |  | R | [6 empty] | A
Admin | Final MVP1 Demo | [8 empty] | I | I | A | [12 empty] | I | I | I | I | I | I | A | bar: A/R to A/R A
Deploy | Document User Guide and FAQ | bar: A/R to A/R R
Admin | Roadmap, high-level plan and business case for subsequent phases | [8 empty] | A | A | A | [16 empty] | A | A | A | bar: A/R to A/R A
Deploy | Change Management and Readiness | bar: A/R to A/R R; A/R C
Deploy | MVP1 Review and Sign-off | [8 empty] | A | A | A | [12 empty] | R | R | R | R | A | A | A | bar: A/R to A/R A
| R = Responsible | Responsible for performing the task (ie. the actual person doing the work to complete the task). | [14 empty] | A/R: Responsible for performing the task (ie. the actual person doing the work to complete the task).
| A = Accountable | Ultimately accountable for the task being done in a satisfactory manner. The accountable person must sign-off the work that the Responsible person produces. | [14 empty] | A/R: Ultimately accountable for the task being done in a satisfactory manner. The accountable person must sign-off the work that the Responsible person produces.
| C = Consulted | Team members whose input is used to complete the task. Communication with these members will be 2-way in nature. | [14 empty] | A/R: Team members whose input is used to complete the task. Communication with these members will be 2-way in nature.
| I = Informed | Team members who are informed as to the status of the task. Communication with these members will be 1-way in nature. | [14 empty] | A/R: Team members who are informed as to the status of the task. Communication with these members will be 1-way in nature.

## High Level Milestones_KD
High Level Milestones | [8 empty] | Definitions of each Phase
# | Phase | High Level Time Horizon | Track for VP+? | Activity | Blue Shield Implementation | Stellarus Product | One and done or sprint by sprint | Timeline | Pre‑Dev / Discovery & Design | Confirm the MVP2 scope, stakeholders, and high‑level requirements to ensure the team is building the right solution.
1 | Pre‑Dev / Discovery & Design | 2 weeks |  | Discovery | A |  | One & Done | 2/27 + 2 weeks | Design | Define the solution approach, data foundations, and user experience needed to support MVP2 delivery.
2 |  | 2 weeks |  | Review existing data | A |  | One & Done | 2/27 + 2 weeks | Build & Iterate | Develop, test, and refine the solution iteratively to meet MVP2 requirements and performance expectations.
3 |  | 2 weeks |  | Identify stakeholders | A |  | One & Done | 2/27 + 2 weeks | Pre‑Deployment | Validate readiness across business, technology, and operations and secure approval to release to production.
Define "projects" for delivery
3 |  | 2 weeks |  | Document high‑level requirements – virtual blue "project" | A |  | One & Done | 2/27 + 2 weeks | Deployment | Release MVP2 to production in a controlled manner and support initial adoption through hypercare.
4 |  | 2 weeks |  | Document high‑level requirements – group products | A |  | One & Done | 2/27 + 2 weeks | Deployment | Release MVP2 to production in a controlled manner and support initial adoption through hypercare.
5 |  | 2 weeks |  | Document high‑level requirements – formulary | A |  | One & Done | 2/27 + 2 weeks | Post‑Deployment / Steady State | Transition the solution to steady‑state operations, monitor adoption, and ensure ongoing performance and refresh.
6 |  | 2 weeks |  | Refresh cycle problem statement | A |  | One & Done | 2/27 + 2 weeks | Admin / Governance | Provide ongoing oversight, status reporting, and risk escalation to ensure timely delivery and decision‑making.
7 |  | 2 weeks |  | Document high level requirements - reinforcement learning | A |  | One & Done | 2/27 + 2 weeks
8 |  | 2 weeks |  | Document requirements enhancing user-facing test application/UI | A |  | One & Done | 2/27 + 2 weeks
9 |  | 2 weeks |  | MVP2 scope confirmed and approved | A |  | One & Done | 2/27 + 2 weeks
10 | Design | 6 weeks? Dependent on above |  | Data model defined |  | A | TBD
10 |  | 4 weeks |  | Detailed requirements/stories for each feature virtual blue "project" |  | A | Sprint | 2 weeks x 6 categories; but 3 categories at a time (4 weeks)
11 |  | 4 weeks |  | Detailed requirements/stories for each feature set/benefit "project" |  | A | Sprint | 2 weeks x 6 categories; but 3 categories at a time (4 weeks)
12 |  | 4 weeks |  | Detailed requirements/stories for formulary |  | A | Sprint
13 |  | 2 weeks |  | Ground truths for benefit "project" | A |  | TBD
14 |  | 2 weeks |  | Ground truths for formulary | A |  | TBD
15 |  | 2 weeks |  | Test Data for benefit category | A |  | TBD
16 |  | 2 weeks |  | Test Data for formulary | A |  | TBD
17 |  | 2 weeks |  | UI enhancement detailed requirements |  | A | One & Done
18 |  | 2 weeks |  | Reporting enhancements defined (if needed) |  | A | One & Done
19 |  | 2 weeks |  | Data readiness confirmed |  | A | TBD
20 |  | 2 weeks |  | Document cycle refresh process requirements |  | A | One & Done
21 |  | 2 weeks |  | Human validation testing approach |  | A | One & Done
22 | Build & Iterate | 4 weeks |  | Data ingestion and transformation |  | A | Sprint?
23 |  |  |  | Model enhancement |  | A | Sprint
24 |  |  |  | Annotation and ground truth evaluation | A |  | Sprint
25 |  |  |  | Human validation testing | A |  | Sprint
26 |  |  |  | UI enhancement testing |  | A | Sprint
27 |  |  |  | Reporting enhancements |  | A | Sprint
28 |  |  |  | Model reinforcement learning |  | A | One & Done
29 | Pre‑Deployment & Readiness |  |  | Business readiness and change management | A |  | One & Done
30 |  |  |  | Reporting ready |  | A | One & Done
31 |  |  |  | Provisioning completed |  | A | One & Done
32 |  |  |  | Hypercare and run responsibilities defined |  | A | One & Done
33 |  |  |  | Go‑live decision / release approval |  | A | One & Done
34 |  |  |  | Signoff | A |  | One & Done
35 |  |  |  | Signoff on cycle refesh process and resources | A |  | One & Done
36 | Deployment |  |  | Limited production deployment |  | A | One & Done
37 |  |  |  | Full production deployment |  | A | One & Done
38 |  |  |  | Hypercare period closes |  | A | One & Done
39 | Post‑Deployment / Steady State |  |  | Steady‑state handoff |  | A | One & Done
40 |  |  |  | Adoption monitoring | A |  | Ongoing Op
41 |  |  |  | Refresh process stood up with controls |  | A | annual?
42 |  |  |  | Post‑deployment success review |  | A | One & Done
43 | Admin / Governance (Ongoing) |  |  | Weekly project updates | A |  | Weekly
44 |  |  |  | Kickoff meeting | A |  | One & Done
45 |  |  |  | Midpoint check‑in | A |  | One & Done
46 |  |  |  | Demo(s) | A |  | Sprint
47 |  |  |  | Final close‑out | A |  | One & Done
48 |  |  |  | Risk escalation for decisioning | A |  | Ad hoc
49 |  |  |  | Update all documentation for teams on cycle refresh | A |  | One & Done
50
51
52
53
54
55
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we define ground truth and test data together?

## Generic Lifecycle
High Level Milestones | [10 empty] | Definitions of each Phase
# | Phase | High Level Time Horizon | Dependency | For VPs? | Step | Activity | Blue Shield Implementation | Stellarus Product | One and done or sprint by sprint | Timeline | Pre‑Dev / Discovery & Design | Confirm the MVP2 scope, stakeholders, and high‑level requirements to ensure the team is building the right solution.
| 0. Project Initiation | 2 weeks | N/A | X | 0.1 | Document high‑level requirements i.e. problem statement and business outcomes | A |  | One & Done
|  |  | 0.1 | X | 0.2 | High Level business case - focus on benefits | A |  | One & Done
|  | 2 weeks | 9.2 | X | 0.3 | Cost Model Assumptoins |  | A | One & Done
|  | 2 weeks | 0.3 |  | 0.4 | Funding approved with cost centers and VP Approval | A |  | One & Done
|  | 2-4 weeks? | 0.4 | X | 0.5 | AI Governance Approval | A | A | One & Done
| 1 Pre‑Dev / Discovery & Design | 2 weeks |  |  | 1.1 | Discovery |  |  | One & Done |  | Design | Define the solution approach, data foundations, and user experience needed to support MVP2 delivery.
[5 empty] | 1.2 | Identify "data" |  |  | One & Done |  | Build & Iterate | Develop, test, and refine the solution iteratively to meet MVP2 requirements and performance expectations.
[5 empty] | 1.3 | Identify stakeholders: SMEs, Data Owners, Testers |  |  | One & Done |  | Pre‑Deployment | Validate readiness across business, technology, and operations and secure approval to release to production.
[5 empty] | 1.4 | Document high‑level requirements i.e. problem statement and business outcomes |  |  | One & Done
|  |  |  | X | 1.5 | Define "projects" |  |  | One & Done |  | Deployment | Release MVP2 to production in a controlled manner and support initial adoption through hypercare.
[5 empty] | 1.6 | Define/Refine business case with KPIs and success measures |  |  | One & Done
[5 empty] | 1.7 | Define high level requirements for dashboards for business value, product mgmt, and model performance |  |  | One & Done
|  |  |  | X | 1.8 | Communicate scope of each project |  |  | One & Done
| 2. Design | 2 weeks |  |  | 2.1 | Define Data model |  | A | Spring
|  | 8 hours SME |  | X | 2.2 | Detailed requirements for the "project" related to model output |  | A | Sprint | 2 weeks x 6 categories; but 3 categories at a time (4 weeks)
|  | 24 hours SME |  |  | 2.3 | Document Ground truths / data dictionary (part of 2.2) include questions the model should NOT respond to |  | A | Sprint | 2 weeks x 6 categories; but 3 categories at a time (4 weeks)
|  | 16 hours SME |  |  | 2.4 | Document Test Data, Scripts, Answer Key (part of 2.2) include questions the model should NOT respond to |  | A | Sprint
[5 empty] | 2.5 | Define Testing Rubric - success vs. fail; nice to have vs. need to have |  |  | Sprint
|  |  |  | X | 2.6 | Detailed requirements on data |  |  | Sprint
[5 empty] | 2.7 | Educate on Human validation testing |  | A | One & Done
|  |  |  | X | 2.8 | Communicate go live criteria for each "project"
| Build & Iterate |  |  |  | 3.1 | Data readiness confirmed |  | A | TBD
[5 empty] | 3.2 | Data ingestion and transformation |  | A | Sprint?
|  |  |  | X | 3.3 | Model build / enhancement |  | A | Sprint
|  |  |  | X | 3.4 | "Iteration" i.e. Annotation and ground truth evaluation |  |  | Sprint
|  |  |  | X | 3.5 | Human validation testing |  |  | Sprint
| Pre‑Deployment & Readiness |  |  | X | 4.1 | Business readiness for Deployment i.e. training, rollout schedule/WFM, change management |  |  | One & Done
[5 empty] | 4.2 | Business readiness for Ongoing Ops i.e. ongoing support model and refresh
[5 empty] | 4.3 | Reporting ready |  | A | One & Done
[5 empty] | 4.4 | Provisioning Process Completed |  | A | One & Done
[5 empty] | 4.5 | Hypercare responsibilities defined; meetings established |  | A | One & Done
[5 empty] | 4.6 | Go‑live decision / release approval for each project |  | A | One & Done
|  |  |  | X | 4.7 | Signoff by Business & IT |  |  | One & Done
| Deployment |  |  | X | 5.1 | Limited production deployment |  | A | One & Done
[5 empty] | 5.2 | Limited Production Focus Group
[5 empty] | 5.3 | Limited Production Reporting/Data-driven Reviews |  | A | One & Done
[5 empty] | 5.4 | Post-Limited Production: Solve for any blockers or prioritize nice to haves
|  |  |  | X | 5.5 | Communicate Limited Production Feedback
|  |  |  | X | 5.5 | Go-live decision for full production
[5 empty] | 5.6 | Full production deployment
[5 empty] | 5.7 | Hypercare period 30-45 days |  | A | One & Done
|  |  |  | X | 5.8 | Post‑deployment success review |  | A | One & Done
| Post‑Deployment / Steady State |  |  | X | 6.1 | Steady‑state handoff |  | A | One & Done
[5 empty] | 6.2 | Adoption monitoring |  |  | Ongoing Op
[5 empty] | 6.3 | Refresh process stood up with controls |  | A | annual?
[5 empty] | 6.4 | Bi-weekly enhancement reviews (until reinforcement learning is deployed)
| Admin / Governance (Ongoing) |  |  |  | A | Weekly project updates |  |  | Weekly
|  |  |  | X | B | Kickoff meeting |  |  | One & Done
|  |  |  | X | C | Midpoint check‑in |  |  | One & Done
|  |  |  | X | D | Demo(s) |  |  | Sprint
|  |  |  | X | E | Final close‑out |  |  | One & Done
[5 empty] | F | Risk escalation for decisioning |  |  | Ad hoc
[5 empty] | G | Update all documentation |  |  | One & Done
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Run by Heather

## Projects
| Subprojects | IFP & SG | Mid & Premier | Prompt or Ground Truth + Prompt | New Source Data? | Other Dev/Config | Example of Use Case | Knowledge Article / Current Process
1 | Virtual Blue Plan for IFP & SG | X | X | Prompt | No |  | As a user, if the member is on a virtual blue plan, I need to quote a $0 tier specifying the coverage for virtual visits with providers in the virtual blue network
2 | Embedded Ind/ Family Deductibleplans for IFP &SG | X | X | Prompt | No |  | As a user, if the member's plan design has Family Embedded Individual, I need to ensure when quoting deductibles I consider than plans with 1 member (individual coverage) vs more than 1 member (family coverage) have different deductible amounts | Example product - M0040921, M0037521
3 | AN-AI plans for IFP | X | ? | Prompt | No |  | As a user, when the member is on a plan where the Facets Product Description includes "AN-AI ", that I'm providing benefits for this network, in-network and out of network (3 tiers of networks) | Example product - MK002188
4 | USPTF Guidelines (change anually) | X | X |  | Yes |  | As a user, I need to the model to look up and pull back the applicable age, gender, and eligibility information that qualifies a preventive benefit so that I do not have to manually reference the document and can better service my customer accurately and quickly
5 | UI enhancements informed by MVP | X | X | N/A |  | Yes | As a user, I need a pinned note to remind me to explain/share all required elements of a complete quote per LOS definitoins, if the customer does not specify a site of care, INN or OON, etc.
6 | Reporting enhancements informed by MVP 1 | X | X | N/A |  | Yes | TBD
7 | Operational Cycle/Admin | X | X |  |  | auto ground truth | As an operational leader, I need to ensure that annual changes ot 'static" data are updated, tested, and changes are made to continue to respond with accurate quotes; as part of product cycle annual refresh work
8 | Formulary | X | X | Ground Truth + Prompt | Yes - annual |  | As a user, I need the model to only respond with the coverage applicable to the tier that the specific drug/medication/prescription falls under, in order to be more accurate and concise in my response to the customer | Customer Experience - Quoting Pharmacy Prescription Benefits.url
9 | LG - Portfolio - A |  | X | Ground Truth + Prompt | No |  | As a user, I need to make sure that fertility can be interpreted and mapped correctly to the Nexus data
10 | LG - Portfolio - B |  | X | Ground Truth + Prompt | No
11 | LG - Portfolio - C |  | X | Ground Truth + Prompt | No
12 | LG - Custom - D |  | X | Ground Truth + Prompt | No
13 | LG - Custom - E |  | X | Ground Truth + Prompt | No
14 | LG - ASO - F |  | X | Ground Truth + Prompt | No
15 | LG - ASO - G |  | X | Ground Truth + Prompt | No
16 | Mira response in spanish | X | X |  | ? |  | As a user, I want to have Mira respond to me in spanish with the benefit quote so that I can speak to my customers easily in spanish?
15 | Real-time accumulator status |  |  |  | Yes API
16 | Real-time utilization of benefits (i.e. how many home health days or PT sessions per claims history) |  |  |  | Yes API
17 | Allowed amounts specific to provider (leverage shawna for what this flow looks like) |  |  |  | Yes |  |  | Researching Allowed Amounts
18 | Helm Provider Tier Lookup |  |  |  | Yes API
19 | provider network lookup |  |  |  | Yes |  |  | https://blueshieldca.sharepoint.com/:f:/r/sites/TOCES/Shared%20Documents/AI%20work/Use%20Case%202.%20Benefit%20Quoting/Benefit%20Quoting%20-%20Process%20Documentation/Determining%20Provider%20Network%20Status?csf=1&web=1&e=EWyVx7
20 | Is a prior authorization required |  |  |  | In nexus? |  |  | Researching Prior Authorization Requirements

## accenture
#VALUE!
| Pre-Dev Activities |  | Role
| Discovery & Design | Review the data | Driver
|  | Identify the stakeholders | Lt Driver
|  | Document high level requirements - group products | Product Manager - Jason?
|  | Document high level requirements - formulary | Scrum Master - was nidhi but is it tami
| Design | Data Model low level requirements - group products incl. ground truths | Product Owner/BSA - Jason?
|  | Data Model low level requirements - formulary incl ground truths | Dev
|  | Training Data Use Cases/Queries |  | Eng
|  | Test data Use Cases/Queries |  | Data Scientist
|  | UI Enhancement Detailed Requirements |  | Prompt eng?
Reporting Enhancements, if needed
Dynamic Reinforcement Learning Requirements
| Build & Iterate | Model Enhancements
Model Annotation/Ground Truth Evaluation
Perform Human Validatoin Testing
UI Enhancement Testing
Reporting Enhancements
Model Reinforcement Learning
| Pre Deployment Activities | Biz Readiness & Change Mgmt
Reporting Ready
Provisioning
Hypercare & Run Responsibilities Defined
Steady State / Run Activities including refresh process
Signoff
| Deployment Activities | Limited Prod
Full Prod
Hypercare Period Closes
Steady State Handoff
Adoption Monitoring
Refresh Process Stood Up with controls
| Admin | weekly project updates
kickoff, mid-point, demo, and final meetings
risk escalation for decisioning