# Blue Shield CA Generative Agent Chat Interface

## Project Plan - BSC Member Pilot Launch

Version: 1.0

Date: March 17, 2026

Prepared by: Julie Hughes

For Review: Stellarus Team

____________________________________________

## Executive Summary

Build a generative agent (GA)) chat interface within the Blue Shield CA member portal focused exclusively on benefits support, with initial pilot launch to BSC employees who have BSC insurance. Future expansion to other lines of business and use cases will take place through 2027.

Key Scope Decisions:

• Benefits support only (excludes claims, billing, other use cases)

• BSC members who are employees as pilot group

• Member portal/Genesys integration

• Sierra.ai for managing the GA

• End of Q2 2026 target launch with BSC Employees (stretch goal, not required by the MEM team)

_______________________________________

## Project Phases Overview (Proposal)

| Phase | Duration | Dates* | Key Activities | Dependencies |
| --- | --- | --- | --- | --- |
| Phase 0: Business Foundation | 6 weeks | Mar 9-Apr 17 | Contract finalization, pricing, governance | Contract negotiations |
| Phase 1: Product Discovery | 3 weeks | Mar 9-27 | MEM and Stellarus team requirements discussions |  |
| Phase 2: Technical Planning and architecture | 3 weeks | Mar 23-Apr 13 | Engineering kickoff and requirements review, architecture | NOT dependent on Phase 0 |
| Phase 3: UX Design | 4 weeks | Apr 6-May 4 | UX design, interface mockups, user flow optimization | Phase 1 complete |
| Phase 4: Core EVP Development | 6 weeks | Apr 13-May 22 | Tech spec, Chat interface, loading knowledge, Sierra configuration | Phase 1 complete |
| Phase 5: QA & UAT | 4 weeks | May 25-Jun 19 | Testing, security validation, performance | Partial Phase 4 overlap |
| Phase 6: Pilot Preparation/Business Readiness | 3 weeks | May 25-Jun 12 | Documentation, training, pilot setup, dashboards | Phase 5 complete |
| Phase 7: BSC Member Pilot | Ongoing | Jun 22 | Pilot launch, monitoring, feedback collection | Phase 5 and 6 complete |
| Phase 8: Iteration and Tuning | Ongoing | July 20+ | Performance tuning, expansion planning | Phase 7 complete |

Total Timeline: ~20-25 weeks (achievable for Q2 2026 end target)

____________________________________________

## Detailed Phase Breakdown

### Phase 0: Business Foundation (6 weeks) - Mar 9-Apr 17

1. Finalize contract between Blue Shield and Stellarus

2. Complete pricing negotiations and agreements

3. Establish project governance and stakeholder communication plan

4. Confirm resource allocation and team assignment

### Phase 1: Product Discovery (2 weeks) - Mar 9-27

MEM and Stellarus team requirements alignment

5. Requirements discussions between MEM and Stellarus teams

6. User needs discovery of BSC members

7. Scope validation and success criteria alignment

8. Stakeholder alignment on product vision and objectives

### Phase 2: Technical Planning and Architecture (3 weeks) - Mar 23-Apr 13

Critical foundation for development phases (NOT dependent on Phase 0)

9. Engineering kickoff with full Stellarus team

10. Architecture deep dive and technical specification refinement

11. Linear stories creation and development planning

12. Technical design review and approval

### Phase 3: UX Design (4 weeks) - Apr 6-May 4

User experience design and interface optimization

15. User persona refinement for BSC employee members and benefits use cases

16. Chat interface wireframes and user flow design (parallel with Phase 4 development)

17. Member portal integration UX design and navigation flow

18. Accessibility compliance review and design adjustments

19. Design system alignment with existing BSC member portal standards

20. Early employee feedback planning and validation strategy development for BSC employee pilot group

### Phase 4: Core EVP Development (6 weeks) - Apr 13-May 22

Foundation chat interface capabilities

21. Project kick offs - Broader BSC team, Stellarus GTM, and BSC GTM alignments and milestone launch

22. Development environment setup and CI/CD pipeline establishment

23. Core chat interface implementation within member portal (parallel with step 24)

24. Loading knowledge and data integration (parallel with step 23)

25. Sierra configuration and system setup

26. Member portal/Genesys integration for chat and session management

27. Resolve critical gaps (parallel with steps 23-26):

• Define generative agent training methodology for BSC member benefits use cases

• Design error handling and customer service escalation workflows

• Establish member portal/Genesys authentication and BSC member identification

28. Initial generative agent training for BSC-specific benefits use cases

### Phase 5: QA & UAT (4 weeks) - May 25-Jun 19

Comprehensive validation and user acceptance testing

29. Comprehensive testing suite development and execution

30. Security validation and member data protection testing (parallel with step 29)

31. Performance testing and optimization for member portal load

32. User acceptance testing with stakeholder (BSC Ops/CE) validation

33. Integration testing with existing member portal systems

### Phase 6: Pilot Preparation/Business Readiness (3 weeks) - May 25-Jun 12

Pilot launch readiness and business preparation

34. Member-facing documentation and help guides

35. Customer service team training on GA chat support processes

36. Internal BSC employee communication about pilot program

37. Dashboards and monitoring setup for pilot tracking

38. Early testing with select BSC employee members (validates Phase 5 outcomes)

### Phase 7: BSC Member Pilot (3 weeks) - Jun 22-Jul 17

Controlled pilot rollout

39. Phased rollout to BSC employees with BSC insurance

40. Real-time monitoring and customer support during pilot

41. Member feedback collection and immediate issue resolution

42. Pilot success validation and expansion readiness review

### Phase 8: Iteration and Tuning (Ongoing) - July 20+

Continuous improvement and future planning

43. Performance monitoring and model tuning for BSC member benefits accuracy

44. BSC member feedback analysis and feature iteration

45. Expansion planning for other lines of business members