Blue Shield CA Generative Agent Chat Interface

Project Plan - BSC Member Beta Launch

Version: 2.0

Date: April 28, 2026

Updated by: Julie Hughes

Previous Version: MEM-GA-Project-Plan.md v1.0

For Review: Stellarus Team

═══════════════════════════════════════════════════════

Executive Summary

Build a generative agent (GA) chat interface within the Blue Shield CA member portal focused exclusively on benefits support, with initial pilot launch to BSC employees who have BSC insurance. Future expansion to other lines of business and use cases will take place through 2027.

Key Scope Decisions:

• Benefits support only (excludes claims, billing, other use cases)

• BSC members who are employees as pilot group

• Member portal/Genesys integration

• Sierra.ai for managing the GA

• End of Q2 2026 target launch with BSC Employees (stretch goal, not required by the MEM team)

═══════════════════════════════════════════════════════

Project Phases Overview - UPDATED

| Phase | Duration | Dates | Key Activities | Dependencies |
| --- | --- | --- | --- | --- |
| Phase 0: Business Foundation | 6 weeks | Mar 9–Apr 17 | Contract finalization, pricing, governance | Contract negotiations |
| Phase 1: Product Discovery | 3 weeks | Mar 9–27 | MEM and Stellarus team requirements discussions |  |
| Phase 2: Technical Planning and Architecture | 3 weeks | Mar 23–Apr 13 | Engineering kickoff, architecture, delivery foundations | NOT dependent on phase 0 |
| Phase 3: UX Design | 4 weeks | Apr 6–May 11 | UX design, interface mockups, user flow optimization | Phase 1 complete |
| Phase 4: Core EVP Development | 6 weeks | Apr 13–May 22 | Chat experience, knowledge integration, Sierra configuration | Phase 1 complete |
| Phase 5: QA & UAT | 4 weeks | May 25–Jun 19 | Testing, security validation, performance | Partial Phase 4 overlap |
| Phase 6: Pilot Preparation/Business Readiness | 3 weeks | May 25–Jun 12 | Documentation, training, escalation, analytics, pilot setup | Phase 5 complete |
| Phase 7: BSC Member Pilot | Ongoing | End of June | Pilot launch, monitoring, feedback collection | Phase 5 and 6 complete |
| Phase 8: Iteration and Tuning | Ongoing | TBD | Performance tuning, expansion planning | Phase 7 complete |

Total Timeline: ~20-25 weeks (achievable for Q2 2026 end target)

═══════════════════════════════════════════════════════

Detailed Phase Breakdown

Phase 0: Business Foundation (6 weeks) - Mar 9-Apr 17

1. Finalize contract between Blue Shield and Stellarus

2. Complete pricing negotiations and agreements

3. Establish project governance and stakeholder communication plan

4. Confirm resource allocation and team assignment

Phase 1: Product Discovery (3 weeks) - Mar 9-27

MEM and Stellarus team requirements alignment

5. Requirements discussions between MEM and Stellarus teams

6. User needs discovery of BSC members

7. Scope validation and success criteria alignment

8. Stakeholder alignment on product vision and objectives

Phase 2: Technical Planning and Architecture (3 weeks) - Mar 23-Apr 13

Critical foundation for development phases (NOT dependent on Phase 0)

Core Technical Planning

9. Engineering kickoff with full Stellarus team

10. Architecture deep dive and technical specification refinement

11. Linear stories creation and development planning

12. Technical design review and approval

Delivery Foundations

13. Confirm chat architecture and delivery approach

14. Decide pilot data source and boundaries

15. Define team ownership and delivery handoffs

16. Finalize pilot success metrics and reporting scope

Phase 3: UX Design (4 weeks) - Apr 6-May 11

User experience design and interface optimization

17. User persona refinement for BSC employee members and benefits use cases

18. Chat interface wireframes and user flow design (parallel with Phase 4 development)

19. Member portal integration UX design and navigation flow

20. Accessibility compliance review and design adjustments

21. Design system alignment with existing BSC member portal standards

22. Early employee feedback planning and validation strategy development for BSC employee pilot group

Phase 4: Core EVP Development (6 weeks) - Apr 13-May 22

Foundation chat interface capabilities

Project Kickoffs and Infrastructure

23. Project kick offs

a. Broader BSC team

b. Stellarus GTM

c. BSC GTM alignments and milestone launch

24. Development environment setup and CI/CD pipeline establishment

Chat Experience

25. Integrate chat entry in member portal

26. Implement authenticated member chat session flow

27. Build core benefits question handling paths

28. Add copy, disclosures, and guardrails

Knowledge and Genesys Integration

29. Connect approved benefits content sources to chat within Sierra

• Knowledge: Plan data and procedures integration

• Data: Member info like MemberID, PlanID connection

30. Build the Knowledge Benefit module/API within the Stellarus Agentic AI platform

31. Connect Knowledge Benefit API to chat within Sierra for starting the Knowledge module within the Stellarus platform

32. Deployment of finalized chat script and Genesys API configuration for portal (Map plan data for member authenticated plan)

33. Genesys to Sierra architect flow and bring your own bot integration

34. Capture member interaction and store in Salesforce CDP

35. Validate scope excludes PHI, PII, and accumulators

36. Resolve critical gaps:

• Define generative agent training methodology for BSC member benefits use cases

• Design error handling and customer service escalation workflows

• Establish member portal/Genesys authentication and BSC member identification

Phase 5: QA & UAT (4 weeks) - May 25-Jun 19

Comprehensive validation and user acceptance testing

37. Comprehensive testing suite development and execution

38. Security validation and member data protection testing (parallel with step 37)

39. Performance testing and optimization for member portal load

40. User acceptance testing with stakeholder (BSC Ops/CE) validation

41. Integration testing with existing member portal systems

Phase 6: Pilot Preparation/Business Readiness (3 weeks) - May 25-Jun 12

Pilot launch readiness and business preparation

Core Pilot Preparation

42. Member-facing documentation and help guides

43. Internal BSC employee communication about pilot program

44. Early testing with select BSC employee members (validates Phase 5 outcomes)

45. Customer service team training on GA chat support processes

46. Prepare employee pilot access and enablement

47. Set transcript retention and operational controls

Analytics and Monitoring

48. Set up Sierra Insights for tracking success metrics

49. Enable transcript review and feedback monitoring in Sierra

Final Validation

50. Run end-to-end validation and launch checklist

Phase 7: BSC Member Pilot (X weeks) - End of June

Controlled pilot rollout

51. Phased rollout to BSC employees with BSC insurance

52. Real-time monitoring and customer support during pilot

53. Member feedback collection and immediate issue resolution

54. Pilot success validation and expansion readiness review

Phase 8: Iteration and Tuning (Ongoing)

Continuous improvement and future planning

55. Performance monitoring and model tuning for BSC member benefits accuracy

56. BSC member feedback analysis and feature iteration

57. Expansion planning for other lines of business members

═══════════════════════════════════════════════════════